1. Phase-Based View 📅

This view breaks down the project by phases (Initiation, Analysis, Design, Implementation, Closure).

- 0.0 Project: Rising Depression and Anxiety in Lithuania (Overall project coordination, scope and results )

- 1.0 Initiation & Management

  - 1.1 Define scope, objectives and constraints

  - 1.2 Confirm team roles and responsibilities

  - 1.3 Develop initial schedule and WBS

  - 1.4 Monitor risks and issues

- 2.0 Problem & Context Analysis

  - 2.1 Review scientific and public-health literature

  - 2.2 Prepare problem tree (causes & effects)

  - 2.3 Analyse Lithuanian statistics and trends

  - 2.4 Identify vulnerable groups

- 3.0 Stakeholder Analysis & Engagem

  - 3.1 Identify and classify stakeholders

  - 3.2 Analyse influence, interest and needs

  - 3.3 Plan engagement and communication

  - 3.4 Validate findings with lecturer

- 4.0 Research / Intervention Design

  - 4.1 Define research/intervention questions

  - 4.2 Select methodology and tools

  - 4.3 Prepare instruments and protocols

  - 4.4 Address ethics and approvals

- 5.0 Data Collection & Implementation

  - 5.1 Sampling and recruitment

  - 5.2 Pilot test instruments

  - 5.3 Full data collection/implementation

  - 5.4 Ensure quality control

- 6.0 Data Analysis, Reporting & C

  - 6.1 Clean and analyse data

  - 6.2 Interpret findings and limitations

  - 6.3 Prepare report and presentation

  - 6.4 Present, reflect and close project

2. Deliverable-Based View 📦

This view organizes the project by major outputs/documents.

- 0.0 Project: Rising Depression and Anxiety in Lithuania (All project deliverables and outputs )

- 1.0 Situation & Problem Analysis Package

  - 1.1 Literature review summary

  - 1.2 Problem tree diagram & explanation

  - 1.3 Context statistics tables (Lithuania)

- 2.0 Stakeholder Analysis Package

  - 2.1 Stakeholder register

  - 2.2 Influence-interest matrix

  - 2.3 Stakeholder engagement plan

- 3.0 Research / Intervention Design Package

  - 3.1 Objectives & indicators sheet

  - 3.2 Methodology & tools description

  - 3.3 Ethical & risk note

- 4.0 Data & Findings Package

  - 4.1 Clean dataset / coded transcripts

  - 4.2 Analysis outputs (tables, charts)

  - 4.3 Interpretation notes

- 5.0 Final Deliverables Package

  - 5.1 Final written report

  - 5.2 Presentation slides

  - 5.3 Annexes and supporting material

3. Organizational-Based View 👥

This view breaks down the project by responsibility (who does what).

- 0.0 Project: Rising Depression and Anxiety in Lithuania (Shared responsibility across participants )

- 1.0 Student Project Team

  - 1.1 Plan and coordinate project tasks

  - 1.2 Conduct literature review and problem tree

  - 1.3 Prepare stakeholder analysis

  - 1.4 Collect, analyse data and draft report

- 2.0 Lecturer / Supervisor

  - 2.1 Approve topic and scope

  - 2.2 Provide methodological guidance

  - 2.3 Review interim deliverables

  - 2.4 Evaluate final outputs

- 3.0 External Stakeholders

  - 3.1 Provide data or statistics (if any)

  - 3.2 Participate in interviews/surveys

  - 3.3 Give feedback on findings

- 4.0 University / Administration

  - 4.1 Provide access to resources (library, tools)

  - 4.2 Ensure ethical and data-protection rules

  - 4.3 Support dissemination (seminars, events)

4. Location-Based View 🗺️

This view is structured by context levels (where activities happen).

- 0.0 Project: Rising Depression and Anxiety in Lithuania (Activities distributed across different context levels )

- 1.0 National Level (Lithuania)

  - 1.1 Review national mental-health statistics

  - 1.2 Analyse national strategies and policies

  - 1.3 Identify nationwide risk factors

- 2.0 Regional / Municipal Level

  - 2.1 Select example region/city for deeper focus

  - 2.2 Gather local data and services mapping

  - 2.3 Identify local risk and protective factors

- 3.0 University / Youth Environment

  - 3.1 Focus on student/youth depression and anxiety

  - 3.2 Collect data from university environment

  - 3.3 Identify gaps in support services

- 4.0 Online / Digital Environment

  - 4.1 Review online resources and helplines

  - 4.2 Assess impact of social media / digital tools

  - 4.3 Explore digital interventions and campaigns

5. Mixed View (Phase + Deliverable) 🔄

This view is a combination of phase and deliverable structure, with Phases on Level 1 and key deliverables on Level 2.

- 0.0 Project: Rising Depression and Anxiety in Lithuania

- 1.0 Analysis Phase

  - 1.1 Situation & problem analysis package

    - Problem tree diagram & explanation

    - Literature review summary

    - Context statistics overview

  - 1.2 Stakeholder analysis package

    - Stakeholder register

    - Influence-interest matrix

    - Engagement plan

- 2.0 Implementation & Reporting Phase

  - 2.1 Data collection & findings package

    - Clean dataset/coded data

    - Analysis tables and charts

    - Interpretation notes

  - 2.2 Final report & presentation package

    - Final written report

    - Presentation slides

    - Annexes